## Sheet1
Task No. | Task Description | Responsible Person | Start Date | Actual End Date | Comments
1 | Problem construction | All | 20-Sep | 10-Oct | 1st Consult: 24 Sep
2 | Team Formation | All | 29-Sep | 4-Oct
3 | Social Media selection | All | 5-Oct | 10-Oct | Selected: YouTube & Reddit
4 | Setup GitHub | Bipul | 5-Oct | 10-Oct | Link: https://github.com/bipulpoudel/Social-Media-Assignment
5 | Setup MS Teams | Sirawich | 5-Oct | 10-Oct | Link: https://teams.microsoft.com
6 | Project planning | Sirawich | 5-Oct | 10-Oct
7 | Setup Consultation | Karim | 5-Oct | 10-Oct | 2nd Consult: 15 Oct, 3rd Consult: 18 Oct
8 | Setup bi-daily meeting | Sirawich | 5-Oct | 10-Oct | via MS Teams
9 | Determine subreddits | All | 10-Oct | 10-Oct | politics / trump / kamalaharris
10 | Reddit Data Extraction | Karim | 10-Oct | 11-Oct
11 | Determine YouTube videos | All | 10-Oct | 10-Oct | 3 videos: debate / Trump interview / Kamala interview
12 | YouTube Data Extraction | Sirawich | 10-Oct | 12-Oct | via Google - YouTube v3 API
13 | Reddit Data Preprocessing | Karim | 10-Oct | 11-Oct
14 | Reddit Basic Analysis | Karim | 10-Oct | 11-Oct
15 | YouTube Data Preprocessing | Sirawich | 10-Oct | 12-Oct
16 | YouTube Basic Analysis | Sirawich | 10-Oct | 12-Oct
17 | Reddit N-grams | Karim | 10-Oct | 15-Oct
18 | Reddit Sentiment Analysis | Karim/Bipul | 10-Oct | 15-Oct
19 | Reddit Topic Modeling | Karim | 10-Oct | 15-Oct
20 | Reddit Visualization | Karim | 10-Oct | 15-Oct
21 | Reddit Graph Modeling | All | 10-Oct | 18-Oct
22 | YouTube N-grams | Sirawich | 10-Oct | 17-Oct
23 | YouTube Sentiment Analysis | Sirawich/Bipul | 10-Oct | 17-Oct
24 | YouTube Topic Modeling | Sirawich/Bipul | 10-Oct | 17-Oct
25 | YouTube Visualization | Sirawich | 10-Oct | 17-Oct
26 | Create report outline | Bipul | 10-Oct | 11-Oct
27 | First draft | Bipul | 10-Oct | 13-Oct
28 | Revise draft | All | 10-Oct | 19-Oct
29 | Formatting and Cleanup | Sirawich | 10-Oct | 20-Oct
30 | Finalizing | All | 10-Oct | 20-Oct
31 | BRAND NEW WOWAOWOOWAOAO | pelae | work | ples | yes